## Sheet1
|  |  |  | Projected Hours | Projected Hours/Asset | Actual Total Hours | Actual Hours/Asset | Actual Cost | Actual Projected Cost | Projected Cost | Projected Total Cost
monsters | 2 | 40 | 5% | 680 | 5 | 4.8714 | 2.4357 | 43.8429 |  | 90 | 1800
backgrounds | 6 | 48 | 12.5% | Projected Hours remaining | 10 | 29.2286 | 4.8714 | 263.0571 |  | 540 | 4140
Total Progress | 8 | 88 | 9.091% | 610 |  | 34.1 |  | 306.9 | 3375.9 | 630 | 5940
|  |  |  | Estimated Hours Remaining | Estimated Hours Total |  |  |  | Current Budget Target
|  |  |  | 375.1 | 409.2 |  |  |  | 56.83%
|  |  |  | Estimated Completion Date | Estimated Total Cost
|  |  |  | Nov 26th | 3682.8